## Project Time Plan
Week | Step | Task Name | Description / Objectives | Start Date | End Date | Status
Week 1 | Step 1 | Initial Setup | README.md + requirements.txt: Write project description, setup instructions, and all required packages | 2026-03-23 | 2026-03-24 | Planned
Week 1 | Step 2 | Data Acquisition | Download dataset: Get Online Retail II from UCI, place in data/raw/ | 2026-03-25 | 2026-03-25 | Planned
Week 1 | Step 3 | EDA Phase | 01_eda.ipynb: Explore data, find patterns, plot charts, understand the dataset | 2026-03-26 | 2026-03-27 | Planned
Week 1 | Step 4 | Preprocessing | 02_preprocessing.ipynb: Clean data, build RFM scores, scale features, save processed CSV | 2026-03-28 | 2026-03-29 | Planned
Week 2 | Step 5 | Clustering Analysis | 03_clustering.ipynb: Run K-Means + DBSCAN, compare, assign segment labels | 2026-03-30 | 2026-03-31 | Planned
Week 2 | Step 6 | Dimensionality Reduction | 04_autoencoder.ipynb: Build deep learning Autoencoder, compress features, recluster | 2026-04-01 | 2026-04-03 | Planned
Week 2 | Step 7 | Model Training | 05_classifier.ipynb: Train Random Forest on cluster labels, save all models as .pkl / .h5 | 2026-04-04 | 2026-04-05 | Planned
Week 3 | Step 8 | Application Development | Build Streamlit app: Write main.py, predict.py, utils.py, components.py | 2026-04-06 | 2026-04-09 | Planned
Week 3 | Step 9 | Deployment | Deploy to Streamlit Cloud: Push to GitHub, connect Streamlit Cloud, get live link | 2026-04-10 | 2026-04-12 | Planned
Week 4 | Step 10 | Documentation & Articles | Report, slides, Medium article: Write final report PDF, 5-10 slides, publish Medium article | 2026-04-13 | 2026-04-18 | Planned